DRAFT

Sanbornton Master Plan Advisory Committee

Meeting Minutes

July 14, 2009

The meeting opened at 7:05 pm with the following members in attendance: Elizabeth Merry, Historic District Commission Representative; Mary Ahlgren, Conservation Commission Representative; Linda Surowick, Fire Department Representative; Grant, Zoning Board of Adjustment Representative; John Thayer, Department of Public Works Representative; Jeff Burns, Energy Committee Representative; Dave Wittham, Sanbornton Historical Society Representative and Bob Ward, Town Planner.

Role Call

As listed above.

Absent were: Steve Ober, Selectman’s Representative; Carmine Cioffi, Planning Board and Building Committee Representative and Corey Robinson, Recreation Commission Representative.

Bob Ward stated that he would like to present a tentative revised schedule for the completion of the Master Plan update. He further stated that he would like to have a draft copy of the Master Plan update for review and approval at the August meeting. Bob Ward stated that a joint meeting with the Planning Board would be scheduled for the Sanbornton Planning Board “Workshop Meeting” on September 3, 2009 to present the draft. He further stated that the Planning Board would then review the draft and present it at a public hearing in November to receive feedback from the community. Bob Ward stated that formal adoption of the updated Master Plan would be completed by the Planning Board after the first of the year. Bob Ward explained that he would like to see the final version of the Master Plan endorsed and signed by the members of the Planning Board as well as by the appropriate boards, committees and departments in Town.

Bob Ward stated that the 1995 Master Plan included a housing section. He further stated that the current data which would be used to complete this section in the 2010 Master Plan is ten years old and that he does not recommend including a housing section in the 2010 edition of the Master Plan. This section could be completed in the future after new 2010 US Census data is available and also after the Workforce Housing issues have been addressed in the Zoning Ordinance.

Bob Ward stated that he is currently is currently in the process of drafting the narrative portion of the 2010 Master Plan. Bob Ward handed out draft copies of the first few sections of the Master Plan Update for review. The MPAC reviewed the Introduction, Vision Statement and Guiding Principles sections of the draft. Discussion followed pertaining to changes in the wording of these sections. Bob Ward stated that he would like the MPAC members to take the draft version of the Master Plan Update home for review and to e-mail proposed changes back to him no later than one week prior to the August meeting.

Bob Ward stated that the remainder of the meeting would involve a mapping exercise involving the future land use map. He further stated that he would like to finish this section up and approve the map by the end of tonight’s meeting. Discussion followed pertaining to proposed Village Districts for the 2010 Master Plan. Bob Ward stated that the qualifications for a Village District are: 1) compact / high density, 2) mixed use and 3) accessibility. The members of MPAC discussed Village Districts and decided to include 1) Winnisquam Village, 2) Chapel Village and 3) Sanbornton Square Village on the Future Land Use map. Discussion pertaining to additional village districts followed.

The meeting adjourned at 9:30 pm.

Respectfully Submitted,

Carole Chase

Recording Secretary