Sanbornton Planning Board

Workshop Meeting

Draft Meeting Minutes

February 4, 2010

1. Role Call

The meeting opened at 7:02 pm with the following members in attendance: Don Bormes, Chairman; Carmine Cioffi, Vice Chair; Peter Dascoulias, Member; Terry Lewis, Alternate and Bob Ward, Town Planner.

Absent were: Steve Ober, Selectmen’s Representative; Dick Gardner, Member; Evelyn Auger, Alternate; Cindy Merchant, Alternate.

2. Seating of Alternates for absent members

Terry Lewis was seated for Dick Gardner.

3. Old Business

a. Update on production schedule for Master Plan

Bob Ward reviewed the progress made by MPAC over the past two years in formulating the update of the Master Plan. Bob Ward stated the Vision (Goals and Objectives) section and the Land Use section have been completed. He further stated that the Planning Board’s review took 3 months to complete, which review was very detailed and the draft went back to MPAC in January. Bob Ward stated that at the February MPAC meeting the production schedule was discussed and there are two options. The first option is to work on an accelerated pace and complete the draft Master Plan in 2-3 months. The second option is to work on an extended schedule so that more input from the public can be obtained and also to hold informational meetings to keep the community informed. Bob Ward stated that the MPAC chose the extended schedule and is now asking the Planning Board to grant approval of the schedule. The extended schedule should take until approximately the end of 2010. Terry Lewis stated that the written portions should be completed fairly quickly, the time consuming factor will be in presenting it to various Boards and the public. Carmine Cioffi made a motion to allow the MPAC to continue the Master Plan process on an extended schedule, seconded by Peter Dascoulias. All in favor, motion carried.

b. Discussion on printing format for new Master Plan

Bob Ward stated that the new Master Plan should be approximately 40-50, 8 ½ x 11 pages. He further stated that he would like to use a 3-ring format and to process the document in house rather than use a commercial printing company. Bob Ward stated that this format will be easier when incorporating new pages and sections into the Master Plan document. He further stated that copies will be provided to all of Sanbornton’s Land Use Boards as well as copies at the Library, Town Offices and online. All Master Plan maps in an 11x17 sheet size and will be printed in house. Fees will be charged for hard copies of the Master Plan. All members of the Planning Board were in agreement that this would be a cost effective process.

4. New Business

a. Discussion re: proposed zoning amendments and schedule of Public Hearings for 2010 Town Meeting

Bob Ward presented the Planning Board members with an outline of proposed zoning amendments as previously discussed. Bob Ward stated that the focus of the proposed amendments is on mapping and not on the text of the Zoning ordinance as in previous years. He further stated that the MPAC would like to wait on proposing the Village Plan Alternative until after the Master Plan is completed and the community can be educated on its purpose and intent before proposing a zoning amendment to be adopted by Town Meeting. The Board reviewed possible zoning map amendments. Bob Ward stated that these would be changes to the Zoning Map, which has not been changed in over 10 years. These changes would comply with the existing (1995) Master Plan and the Master Plan Community Survey. Peter Dascoulias suggested providing some type of explanation as to what the changes would mean.

b. Approval for change of Sanbornton Planning Board representative on Master Plan Advisory Committee (from Carmine Cioffi to Terry Lewis)

Carmine Cioffi stated that he would like to step down as the Planning Board representative to MPAC and suggested that the Board appoint Terry Lewis in his place. Peter Dascoulias made a motion to appoint Terry Lewis as the Planning Board representative to MPAC, seconded by Carmine Cioffi. All in favor, motion carried.

c. Review and approval of Planning Board’s Annual report for Town report

Bob Ward handed out a draft of the Planning Board report for the Town’s Annual Report for review. The Planning Board will approve at the next meeting.

d. Review meeting attendance record of Planning Board members for 2008-2009

Bob Ward handed out a copy of attendance at Planning Board meetings as previously requested by the Chairman.

6. Planners Update

None.

7. Adjournment

Carmine Cioffi made a motion to adjourn, seconded by Peter Dascoulias. All in favor, motion carried.

Meeting adjourned at 8:54 pm.

Respectfully Submitted,

Carole Chase

Recording Secretary